TSD MASTER OPERATING PLAYBOOK

How We Operate

The source of truth for how work moves at TSD.

AUDIENCE

All Team Members

VERSION

Version 6

REVISED

May 7, 2026

What changed in Version 6

Version 6 absorbs three sprints of doctrine evolution since v5 and closes the Pass 1 plus Pass 1.5 cross-reference integrity gaps. v6 supersedes v5 and Patch Memos v2.1 and v3.1 (which were absorbed into ADS Playbook v3.1 and VIDEO Playbook v4 respectively).

Sprint 2 absorption  |  Cross-divisional video workflow

- Pre-Shoot Cross-Divisional Roadmap. Vince compiles five inputs from SEO, Paid Ads, Web Dev, and Onboarding Manager 2 weeks before any client video shoot. Without a complete roadmap the shoot does not proceed.

- Green Light Trigger. Vince's single ClickUp Final Approved confirmation fires four parallel handoff tickets: S-VLOG-PUB, W-VIDEOEMBED, A-CAMPAIGN-ACT, S-PHOTOEXTRACT.

- YouTube upload. V-YOUTUBE prerequisite ticket. Owned by Video team using SEO-written YouTube brief from client Drive folder. SEO writes the brief; Video executes the upload. Resolved doctrine, no longer pending.

- R8 Post-Shoot Photo Extraction. SEO extracts photos from B-roll capture and shoot stills, uploads minimum 10 to GBP, confirms LSA sync with Manuel within 48 hours of Green Light.

Sprint 3 absorption  |  v5.1 patch

- A4 Weekly Paid Ads Pulse, R9 Weekly SEO Pulse, W4 Weekly Web Dev Pulse. Standardized Friday 9 AM roll-up tables covering all active clients with health flag (Green/Yellow/Red) and 5 essentials per client. Replaces ad-hoc 'how is X doing this week' Slack threads. Will be automated by Agency Titan in a future wave.

- A5 Quarterly Paid Ads Strategy Review, R10 Quarterly SEO Strategy Review. Per-client deep dives delivered by Day 10 of new quarter. Land in AM Account Health Review. Cover what worked, what did not, top 3 strategic recommendations with budget or content roadmap implications.

- AM Aggregator Block. AMs receive 3 weekly inbound feeds (Paid Ads Pulse, SEO Pulse, Web Dev Pulse) and 2 quarterly inbound feeds (Paid Ads Strategy Review, SEO Strategy Review). AMs paste relevant client rows into Friday updates and Account Health Reviews.

- Red row triage doctrine. Any Red health flag in any weekly Pulse triggers AM contacting client within 48 hours with the issue identified and a remediation plan. Yellow flags noted in Friday update only. Green flags require no action.

- TTR Protocol (Time To Resolution). New Section 8. Defines acknowledge SLAs, resolve SLAs, and escalation timelines for every ticket category and emergency type.

Cross-division RACI and handoff SLA cutoff times

- Formal cross-division RACI matrix (Section 7) absorbing the work the WEB Charter v2 was waiting on.

- Landing page handoff SLA cutoff times defined at MasterOps layer (briefs, copy, assets, integrations, launch requirements).

- Cross-division handoff SLAs for the four parallel handoff tickets locked at 48 hours, 5 business days, and 5 business days respectively per ticket type.

Doctrinal-coherence and authoring fixes

- Source-of-truth table updated to consolidated 3-doc CS architecture (AM Playbook v2.1 plus Onboarding Manager Playbook v2 plus Architecture Confirmation Memo v2). Removes ghost references to AMOps v5 and CS Playbook v7.

- All version references throughout v6 reflect current state (no v3, v4, v5 references to docs that have advanced).

- New Section 9: Drive title rename doctrine (OPTION 3). On every patch sprint, Drive titles match internal versions using underscore convention (v5_1, v2_2). Backfill of 6 existing patched docs scheduled in Wave 2 of current sprint.

- New Section 9: Patch authoring template standard. The predecessor footer paragraph is REPLACED, not preserved alongside the new one. Closes Pattern 1 from the Pass 1.5 audit.

Version 6 supersedes Version 5 v5 Patch Memos v2.1 and v3.1 are obsolete and should be archived. ADS Playbook v3.1 and VIDEO Playbook v4 absorbed them. The current operating system is the parent docs plus this MasterOps v6.

What this document is

This is the TopServ Digital Master Operating Playbook. It tells every member of this team how we operate, who owns what, how requests move between divisions, and what the standards are for delivery and communication. This document is not a suggestion. It is how TSD operates.

Each division has its own detailed Playbook with full process documentation, SLAs, and ticket taxonomies. Each division also has a Brandformance Overlay defining the strategic philosophy (the WHY) and a Division Head Operating Charter defining the seat's authority and rhythm. The reading order for any division is: Overlay, then Charter, then Playbook, then this document for cross-division context.

GHL Integrations is a peer specialist seat held by Mo. The role definition (TSD_GHL_RoleDefinition_v1) is the operating standard for that seat.

This Master Operating Playbook is a living document. It is updated as the team structure, tools, and processes evolve.

Section 1  |  Core operating principles

Six principles sit above every process in this document. When the process and the principles conflict, the principles win.

1. The customer comes first. Always. Whatever the process says, the goal is that the client is taken care of. If the process is slowing down client care, escalate to the COO immediately. Do not stall on ownership debate while a client sits with broken work. Get the customer taken care of first, then we clean up the process.

2. AMs own the client relationship including communication. The AM is the single point of accountability for their client's experience. AMs own the client relationship including communication. AMs own coordination across divisions for routine client work. AMs are not relays who connect clients with the right Division Head. AMs run the relationship. Division Heads and Mo are pulled into client calls only when genuinely necessary for technical depth or strategic input. Default: AM runs the call. Exception: AM brings in a DH or Mo for a specific reason. The exception is not the default.

3. Tickets route to the division, not to the Division Head personally. Tickets are submitted to the division's ticket section (or to Mo's GHL Integrations section). The Division Head or Mo is responsible for ensuring the work is acknowledged, assigned, and completed to standard. The Division Head is not the default assignee on every ticket. They are the leader who owns the outcome.

4. AMs own coordination for routine cross-division work. When a client request requires work from multiple divisions, the AM breaks the request into tasks and submits a ticket to each division separately. The AM follows up on timelines. The AM manages tasks across divisions for their client's work. Division Heads do not coordinate with each other for routine work that originated from an AM. That is the AM's job. The narrow exception: when a DH has made a commitment to a client on a call (a transitional reality while DHs are still on calls), the DH who made the commitment owns driving it to completion across divisions. Target state: DHs are not on client calls by default, so DH-to-DH coordination is rare.

5. Route by who does the work, not by which platform is named. Most routing mistakes happen because an AM sees a platform name (Meta, Google Ads, Google Tag Manager, GHL) and routes to the division associated with that platform. That is the wrong test. The right test is: what has to actually happen to fix this, and who does that work? If the fix requires editing the website, it goes to Web Dev even if the alert came from Google. If the fix requires changing a campaign or platform setting, it goes to Paid Ads. If the fix requires GHL configuration, it goes to Mo.

6. GHL components require Mo's Verified Live before client communication. GHL Integrations is a peer specialist seat held by Mo, reporting directly to the COO and accountable peer-to-peer with all Division Heads. Mo is not under any single division. For any work that includes a GHL component (campaign launch with form integration, automation build, pipeline configuration, A2P, DNS for GHL email, Stripe, Voice AI, Conversation AI), Mo holds sole authority to mark the work Verified Live and to close the ticket once both the originating division and Mo have confirmed end-to-end via joint test. AMs do not communicate 'campaign live' or 'automation live' to the client until Mo's Verified Live confirmation is in the ticket.

Section 2  |  Tickets vs recurring processes

Read this carefully These are two different things. Don't confuse them. Most operational confusion at TSD comes from blurring the line. Lock this in.

| DIMENSION | TICKET | RECURRING PROCESS |
| --- | --- | --- |
| What it is | A discrete request for a one-off task. | Scheduled work that fires on a cadence for every eligible client. |
| Who initiates it | AM (or sometimes a DH on a client-call commitment). | The schedule. Triggers automatically when the cadence hits. |
| Has an SLA | Yes. Acknowledgement SLA per ticket category. Standard end of business day. Emergency 1 hour. | No SLA in the same sense. Has a cadence (monthly, weekly) and a Done When definition. |
| Where the standard lives | Section 4 of each Division Playbook (Ticket Types and SLAs). | Section 5 of each Division Playbook (Recurring SOPs). |
| Examples | Update GBP description for ABC Plumbing. Pause Meta campaign tomorrow. Fix 404 on about page. Build new landing page. | Monthly SEO Optimization. GBP Monthly Optimization. Weekly Paid Ads Pulse. Weekly SEO Pulse. Weekly Web Dev Pulse. Quarterly SEO Strategy Review. Monthly Vlogs. |
| Output | The completed task. AM closes the loop with client. | A report, a queue of follow-up items, a published asset, a status update. Output flows back through AM (see Section 3 Recurring Process Output Doctrine). |

Section 3  |  Recurring process output doctrine

Every recurring process produces output. That output flows back through the AM. Always. The AM communicates relevant findings to the client. The AM is never blindsided. The AM is the single point of accountability for client experience.

Hard rule The output of every recurring process is delivered to the AM. The AM is responsible for deciding what to communicate to the client and how. Division Heads and Mo do not communicate recurring process findings directly to clients. The AM may surface findings as part of a regular monthly check-in, an Account Health Review, a quarterly business review, or an ad-hoc Slack message. The cadence and method are the AM's call. The default is: keep the client informed, never let them be surprised.

Recurring process output flow by division

Every recurring process operating in v6. This is the canonical map.

| RECURRING PROCESS | DIVISION | OUTPUT FLOWS TO | WHAT THE AM DOES WITH IT |
| --- | --- | --- | --- |
| Friday AM Status Update | CS | Eve (CS DH) | AM submits. Eve aggregates and flags at-risk to COO. |
| Monthly Account Health Review | CS | Eve oversight | AM conducts. Same-day at-risk escalation if needed. |
| Email and Social Media Production (transitional) | CS | AM (own work) | AM produces and publishes. Flags client review where needed. Q3 2026 structural fix targeted. |
| Client Offboarding | CS | All divisions execute | AM owns client communication throughout. Eve drives execution. |
| R1 Content Production (Monthly Pages) | SEO | AM (notification on publish) | AM communicates new content to client. |
| R2 GBP Monthly Optimization | SEO | AM (negative reviews same-day; significant drops same-day; monthly summary) | AM communicates flags immediately. Monthly summary at month-end. |
| R3 Monthly SEO Optimization | SEO | AM (full optimization report) | AM communicates ranking trends, flags decay, presents refresh queue. Refresh items feed back into R1 next cycle. Technical issues become Web Dev tickets. |
| R4 Automated Backlink Campaign | SEO | AM (monthly summary) | AM communicates new backlinks earned, DR distribution. |
| R5 Reddit Activity | SEO | AM (occasional summary) | AM aware of activity. No regular client communication unless client asks. |
| R6 Press Releases | SEO | AM (placement summary on distribution) | AM communicates placements to client. Sends links. |
| R7 Vlog Production Coordination | SEO + Video | AM (delivery notification + Green Light Trigger) | AM communicates new vlog to client. Coordinates 4 parallel handoff tickets to closure. |
| R8 Post-Shoot Photo Extraction | SEO | AM (48hr from Green Light) + Manuel (LSA sync) | AM confirms photos uploaded to GBP. Manuel confirms LSA sync. |
| R9 Weekly SEO Pulse | SEO | AM (Friday 9 AM) | AM pastes client rows into Friday update. Red rows trigger 48hr client outreach. |
| R10 Quarterly SEO Strategy Review | SEO | AM (Day 10 of new quarter) | AM reviews with DH within 5 business days. Lands in Account Health Review. |
| A1 Weekly Paid Ads Optimization | Paid Ads | AM (within 2 hours of any issue identified) | AM never blindsided on calls. Slack DM same-day for any issue. |
| A2 Biweekly Paid Ads Review | Paid Ads | AM (summary, Accelerator/Dominator only) | AM communicates trends to client at next check-in. |
| A3 Monthly Paid Ads Performance Report | Paid Ads | Manuel signs off, AM delivers | AM presents report to client. |
| A4 Weekly Paid Ads Pulse | Paid Ads | AM (Friday 9 AM) | AM pastes client rows into Friday update. Red rows trigger 48hr client outreach. |
| A5 Quarterly Paid Ads Strategy Review | Paid Ads | AM (Day 10 of new quarter) | AM reviews with DH within 5 business days. Lands in Account Health Review. |
| V1 Monthly Vlogs | Creative/Video | AM (delivery) | AM coordinates publication and client communication. |
| V2 Video Edit / Revision | Creative/Video | AM (per ticket completion) | AM communicates revised asset to client. |
| W1 Monthly Website Health Check (DRAFT) | Web Dev | Justin to AM (summary) | AM aware of any health issues. Escalates if client-facing. |
| W2 Monthly Tracking Audit (DRAFT) | Web Dev | Justin to AM (summary) | AM aware of any tracking gaps. Coordinates fixes via tickets. |
| W3 Monthly Dashboard Maintenance (DRAFT) | Web Dev | Justin to AM (notification of access changes) | AM aware. Re-shares access link with client if changed. |
| W4 Weekly Web Dev Pulse | Web Dev | AM (Friday 9 AM) | AM pastes client rows into Friday update. Tracking-integrity Reds trigger immediate triage. |
| GHL Verified Live Confirmations | GHL Integrations (Mo) | Originating division (Manuel/Justin) + AM | AM communicates campaign or build live to client only after Mo's Verified Live. |

Pattern lock Notice the pattern: every output flows to the AM. Every. Single. One. Even when the originating Division Head signs off internally (Manuel signs off on the Monthly Paid Ads Performance Report, Mo signs off on Verified Live), the AM is the conduit to the client. This is the AM ownership doctrine in action. AMs are not relays. AMs are the relationship. The recurring processes feed AMs the data and decisions they need to run the relationship well.

Section 3.5  |  AM Aggregator Block

New in v6. AMs receive 5 standardized inbound feeds. Three weekly. Two quarterly. The Aggregator defines what AMs receive, when they receive it, and what they do with it. Replaces ad-hoc 'where do I find X' confusion.

Weekly inbound feeds  |  3

| FEED | FROM | TIMING | WHAT AM DOES |
| --- | --- | --- | --- |
| A4 Weekly Paid Ads Pulse | Manuel (Paid Ads DH) | Friday by 9 AM in #paid-ads-pulse | Paste client rows into Friday update. Red rows trigger 48hr client outreach with issue + remediation plan. |
| R9 Weekly SEO Pulse | Alejandro (SEO DH) | Friday by 9 AM in #seo-pulse | Paste client rows into Friday update. Red rows trigger 48hr client outreach. |
| W4 Weekly Web Dev Pulse | Justin (Web Dev DH) | Friday by 9 AM in #webdev-pulse | Paste client rows into Friday update. Tracking-integrity Reds trigger immediate triage (silent tracking breakage erodes Paid Ads CPL). |

Quarterly inbound feeds  |  2

| FEED | FROM | TIMING | WHAT AM DOES |
| --- | --- | --- | --- |
| A5 Quarterly Paid Ads Strategy Review | Manuel (Paid Ads DH) | Day 10 of new quarter, one Google Doc per active client | Review with DH within 5 business days. Land in Account Health Review meeting. AM may request edits before client delivery. |
| R10 Quarterly SEO Strategy Review | Alejandro (SEO DH) | Day 10 of new quarter, one Google Doc per active client | Same as above. Land in Account Health Review meeting. |

Red row triage doctrine

Red flag = 48 hour client contact requirement Any Red health flag in any weekly Pulse triggers AM contacting client within 48 hours with the issue identified and a remediation plan. Yellow flags noted in Friday update only. Mention in next AM-Client touchpoint if it persists. Green flags require no action. AM does not wait for the next scheduled check-in to address a Red. The Red is the trigger.

Section 4  |  Who we are and how we deliver

TopServ Digital

TopServ Digital is a digital marketing agency exclusively serving home service contractors: HVAC, plumbing, electrical, garage doors, concrete coating, solar, and more.

Our unfair advantage is Brandformance.

Brandformance is not a framework we sell. It is the architecture we own and execute for clients. It has three pillars:

- Architecture: the strategic foundation we build for every client.

- Execution: video-first TAYA content, ads, and web, delivered through a defined system.

- Evolution: continuous optimization based on data, not gut feel.

Roles and responsibilities

| ROLE | RESPONSIBILITY |
| --- | --- |
| Founder / CEO | Primary on-camera voice, client relationships, brand vision. |
| COO | Revenue architecture, operations, team accountability, process ownership, sales leadership. |
| CFO | Finance, invoicing, payroll. |
| CS Division Head | Customer Success division, AM oversight, onboarding coordination. |
| Onboarding Manager | Client onboarding execution, Agency Titan, client communication channel management. |
| Account Managers | Client relationship ownership including communication. Project coordination across divisions for their clients. Ticket submission and follow-up. Recurring process output communication to client. AM Aggregator Block consumption. |
| SEO Division Head | SEO strategy, GBP optimization, content plan, TAYA execution, YouTube brief authoring. Source of truth: SEO Playbook v4.1. |
| Paid Ads Division Head | Google, Meta, YouTube, TikTok, LSA campaign management. Graphic Designer management. Source of truth: Paid Ads Playbook v3.1. |
| Web Dev Division Head | Website publishing, tracking install on the website, Agency Analytics technical build, Web Dev side of chatbot install. Source of truth: Web Dev Playbook v3. |
| GHL Integrations Specialist | Mo. Peer specialist seat. GHL pipeline, automations, A2P, DNS, Stripe, Voice AI, Conversation AI. Sole authority on Verified Live. Source of truth: GHL Role Definition v1. |
| Creative / Video Division Head | Video production, video editing, brand creative, YouTube upload execution. Source of truth: Video Playbook v4. |

Program tiers

Every client is enrolled in one of four Brandformance program tiers. The tier determines what they receive and at what volume. Account Managers must know their clients' tier at all times.

| TIER | MONTHLY | KEY DELIVERABLES |
| --- | --- | --- |
| Brand Starter | $2,000 + $3-5k ad spend | Performance marketing only. Minimal onboarding. No video shoot. Automated via AT. Funnel to Builder within 6-9 months. |
| Brand Builder | $5,000 + ad spend | SEO pages (4/mo), GBP (4 posts/mo), 1 vlog every other month, 12 SEO videos at shoot, Monthly SEO Optimization, press releases (3/year). |
| Brand Accelerator | $8,000 + ad spend | SEO pages (10/mo), GBP (8 posts/mo), 1 vlog/mo, 12 SEO videos at shoot, email included, Monthly SEO Optimization, Automated Link Building, Reddit Activity, press releases (6/year). |
| Brand Dominator | $10,000 + ad spend | SEO pages (20/mo), GBP (16 posts/mo), 2 vlogs/mo, 24 SEO videos at shoot, email included, Monthly SEO Optimization, Automated Link Building, Reddit Activity, press releases (12/year). |

How requests move  |  The ticket system

Rule Every structured deliverable request goes through a ticket. No exceptions. Slack is for emergencies and direct escalation or communication only. If it is not in a ticket, it does not exist and it will not be actioned.

The 5-step ticket flow

| # | WHO | WHAT HAPPENS |
| --- | --- | --- |
| 1 | AM | Client asks for something or AM identifies an issue. AM determines if it is a CS lane issue. If yes, handle it. If no, the AM assesses which division(s) need to act and in what order. |
| 2 | AM | AM creates a ticket in each division that needs to do work, in the correct sequence. All 7 fields required on every ticket. |
| 3 | Division | The receiving division (or Mo for GHL Integrations) acknowledges per the TTR Protocol (Section 8). Standard end of business day. Urgent same business day. Emergency within 1 hour. |
| 4 | AM | AM coordinates across divisions for routine work. AM sequences linked tickets, watches the upstream SLA, ensures the deliverable arrives in the next division ready to execute. |
| 5 | Mo (when applicable) | If the work includes a GHL component, Mo holds sole authority on Verified Live. Joint test required. AM does not communicate live to client until Mo's Verified Live is in the ticket. |

The 7-field ticket format

Every ticket must include all seven fields in the task description. Incomplete tickets are returned to the AM without action.

| FIELD | WHAT TO INCLUDE |
| --- | --- |
| CLIENT | Client name exactly as it appears in the ticket system. |
| CATEGORY | Exact ticket category from the division's taxonomy. |
| REQUEST | Specific action required. Exact. Not vague. |
| PRIORITY | Standard or Urgent. |
| CLIENT APPROVED | Yes / No / Not Required. |
| CONTEXT | Background the division needs to act without asking follow-up questions. |
| NEEDED BY | Date or ASAP with the reason why. |

Emergency protocol An emergency is any issue actively causing client harm right now. Mark the ticket URGENT and Slack DM the Division Head (or Mo for GHL emergencies) immediately. Acknowledgement within 1 hour. Resolve per TTR Protocol Section 8.

Section 5  |  The operating units

Five divisions plus one peer specialist seat. Each has its own comprehensive Playbook. The Playbook is the source of truth for that unit's operations. This Master Operating Playbook is the cross-unit context.

| UNIT | PLAYBOOK / SOURCE OF TRUTH |
| --- | --- |
| Customer Success | TSD_DIV_CS_AccountManager_Playbook v2.1 + TSD_DIV_CS_OnboardingManager_Playbook v2 + TSD_ARCH_CS_Confirmation_Memo v2 |
| SEO / GBP | TSD_DIV_SEO_Playbook v4.1 |
| Paid Ads | TSD_DIV_ADS_Playbook v3.1 |
| Web Dev | TSD_DIV_WEB_Playbook v3 (W1/W2/W3 Section 5 DRAFT pending Justin review) |
| GHL Integrations (Mo) | TSD_GHL_RoleDefinition v1 |
| Creative / Video | TSD_DIV_VIDEO_Playbook v4 |

Customer Success

Mission: Own the client relationship from contract signed through the life of the account. AM owns relationship including communication. Project coordination across divisions for routine client work.

Recurring processes: 4 (Friday Status, Account Health Review, Email/Social transitional, Offboarding). See AM Playbook v2.1 Section 5 for execution. Onboarding execution lives in OnboardingManager Playbook v2.

SEO / GBP

Mission: Own organic visibility for every client. Build the content authority that makes TSD clients the most findable, most trusted, most authoritative brands in their markets.

Recurring processes: 10 documented in SEO Playbook v4.1 Section 5.

| # | PROCESS | FREQUENCY | TIERS |
| --- | --- | --- | --- |
| R1 | Content Production (On-Site Pages) | Monthly | All tiers |
| R2 | GBP Monthly Optimization (incl. posting) | Monthly | All tiers |
| R3 | Monthly SEO Optimization | Monthly | Builder, Accelerator, Dominator |
| R4 | Automated Backlink Campaign | Monthly | Accelerator, Dominator |
| R5 | Reddit Activity | Weekly | Accelerator, Dominator |
| R6 | Press Releases | Per tier annual cadence | Builder, Accelerator, Dominator |
| R7 | Vlog Production Coordination | Per tier cadence | Builder, Accelerator, Dominator |
| R8 | Post-Shoot Photo Extraction | Per shoot, triggered by Green Light | Builder, Accelerator, Dominator |
| R9 | Weekly SEO Pulse to AMs | Weekly. Friday by 9 AM. | All tiers |
| R10 | Quarterly SEO Strategy Review | Quarterly. Day 10 of new quarter. | All tiers |

Paid Ads

Mission: Own paid campaign performance across all platforms. Every dollar of client ad spend managed with intent, tracked with precision, reported transparently. No surprises for AMs or clients.

Recurring processes: 5 documented in Paid Ads Playbook v3.1 Section 5. Mo Verified Live gate applies to GHL-touching campaigns.

| # | PROCESS | FREQUENCY | TIERS |
| --- | --- | --- | --- |
| A1 | Weekly Paid Ads Optimization | Weekly | All clients with active campaigns |
| A2 | Biweekly Paid Ads Review | Every 14 days | Accelerator, Dominator |
| A3 | Monthly Performance Report and Strategy Review | Monthly | All clients with active campaigns |
| A4 | Weekly Paid Ads Pulse to AMs | Weekly. Friday by 9 AM. | All active clients |
| A5 | Quarterly Paid Ads Strategy Review | Quarterly. Day 10 of new quarter. | All active clients |

Web Dev

Mission: Own the website infrastructure every client runs on. Website publishing, tracking install on the website, reporting dashboards, Web Dev side of chatbot install.

Recurring processes: 4 in Web Dev Playbook v3 Section 5. W1/W2/W3 DRAFT pending Justin review. W4 active.

| # | PROCESS | FREQUENCY | STATUS |
| --- | --- | --- | --- |
| W1 | Monthly Website Health Check | Monthly | DRAFT - Justin to confirm |
| W2 | Monthly Tracking Audit | Monthly | DRAFT - Justin to confirm |
| W3 | Monthly Dashboard Maintenance | Monthly | DRAFT - Justin to confirm |
| W4 | Weekly Web Dev Pulse to AMs | Weekly. Friday by 9 AM. | Active |

Critical boundary Web Dev does NOT own GHL configuration. GHL is owned by Mo per GHL Role Definition v1. Web Dev installs the chatbot embed on the website. Mo configures the bot. Joint test required for any cross-cutting work.

GHL Integrations  |  Peer specialist seat

Specialist: Mo. Reports to: COO. Peer to all Division Heads.

Mission: Own all GHL configuration and integration work. Hold the Verified Live gate on any client work that includes a GHL component. Joint test with originating division before any GHL-touching campaign or build goes live to client.

Recurring processes: 2 covered in GHL Role Definition v1 (Verified Live confirmations per campaign or build, ongoing automation maintenance per ticket).

Creative / Video

Mission: Own every video asset TSD produces for clients. Video shoots that tell the brand story. Edits that land on time. Video assets that flow to Paid Ads for campaigns. YouTube uploads using SEO-written briefs.

Recurring processes: 2 in Video Playbook v4 Section 6.5.

| # | PROCESS | FREQUENCY | TIERS |
| --- | --- | --- | --- |
| V1 | Monthly Vlogs | Per tier cadence | Builder, Accelerator, Dominator |
| V2 | Video Edit / Revision | Per ticket, 48hr standard SLA | All tiers |

Section 6  |  Cross-divisional video workflow

New in v6. The Pre-Shoot Cross-Divisional Roadmap, the Green Light Trigger, and the four parallel handoff tickets. The single biggest cross-division process in the operating system. Triggered by the Proud Pops post-mortem. Documented at MasterOps layer because it spans every division.

6.1  |  The Pre-Shoot Roadmap

Before any client video shoot, the Creative/Video Division Head compiles a Pre-Shoot Roadmap from five required inputs. Without a complete roadmap, the shoot does not proceed.

| # | INPUT | OWNER | DUE BEFORE SHOOT |
| --- | --- | --- | --- |
| 1 | SEO Video-to-Page Map (S-VIDEOMAP). Every scripted video mapped to a destination URL. | Alejandro (SEO DH) | 2 weeks before shoot |
| 2 | Paid Ads Creative Asset List (A-PRESHOOT). Campaigns waiting on creative, format requirements per platform, hooks, CTAs, compliance flags. | Manuel (Paid Ads DH) | 2 weeks before shoot |
| 3 | LSA Photo Capture List. Photo subjects to be captured during the shoot for GBP and LSA upload. | Alejandro (SEO DH, owns GBP and LSA photos) | 1 week before shoot |
| 4 | Web Dev Page Readiness. Confirms which destination pages from input 1 are live, which need to be built. | Justin (Web Dev DH) | 1 week before shoot |
| 5 | Onboarding Manager confirmation. New clients only. Confirms shoot is scheduled within onboarding 30-day window and Drive folders are ready. | Marlo (Onboarding Manager) | 1 week before shoot |

Roadmap is the contract If the Pre-Shoot Roadmap is not complete 1 week before the shoot, the shoot does not proceed. The roadmap is the contract that ensures every consuming division knows what they will receive and how they will use it. Without it, content gets delivered with no defined home. Vince escalates to COO if any input is missing 1 week before the shoot.

6.2  |  The Green Light Trigger

A single approval point. Vince marks shoot deliverables Final Approved in ClickUp. This is the single source of 'go' for downstream divisions.

What is and is not a Green Light Green Light = every video and every photo intended for distribution is in the client Drive folder, named per file naming convention, and Vince has personally Final Approved in ClickUp. NOT a Green Light: raw footage uploaded. Edits in progress. Vlogs delivered but ad cutdowns still pending. Final delivered but Vince has not personally reviewed. Vince does not delegate the Green Light. Vince's confirmation is the gate.

6.3  |  The four parallel handoff tickets

AM creates all four within 24 hours of Green Light. AM tracks all four to completion. AM's monthly Account Health Review confirms all four closed for any client whose shoot was green-lit in the prior month.

| # | TICKET | RECEIVING DIVISION | WHAT THEY DO | SLA |
| --- | --- | --- | --- | --- |
| 1 | S-VLOG-PUB (Vlog Transcription + Blog Publishing) | SEO + Web Dev | Transcribe vlogs to blog posts. Format with H1/H2, embedded video, internal links. Web Dev publishes on destination URLs from Roadmap. | 5 business days from Green Light to live blog |
| 2 | W-VIDEOEMBED (Website Video Embed) | Web Dev | Embed YouTube-uploaded videos on destination pages from the Roadmap. | 48 hours from YouTube upload |
| 3 | A-CAMPAIGN-ACT (Paid Ads Campaign Activation) | Paid Ads | Cut down master videos to platform-specific aspect ratios. Activate or refresh waiting campaigns. Mo Verified Live gate applies for GHL-routed campaigns. | 5 business days from Green Light to live campaigns |
| 4 | S-PHOTOEXTRACT (LSA + GBP Photo Upload) | SEO | Extract photos from B-roll capture and shoot stills. Upload minimum 10 to GBP. Confirm LSA sync with Manuel. | 48 hours from Green Light |

6.4  |  YouTube upload as prerequisite

Owned by Video team using SEO-written brief YouTube upload (V-YOUTUBE) is not a separate parallel handoff. It is a prerequisite that runs between Green Light and tickets 1, 2, and 3. The Video team uploads videos to YouTube using the SEO-written YouTube brief that lives in the client Drive folder (named ClientName_YouTubeBrief_YYYYMMDD.docx). The brief includes SEO-optimized title, description, tags, thumbnail spec, and destination URL for embed coordination. YouTube upload SLA: 48 hours from Green Light. Tickets 1 (transcription), 2 (website embed), and 3 (campaign activation) reference YouTube URLs. Therefore those tickets cannot fully complete until YouTube upload is done. The 48-hour YouTube SLA is the constraint. Why Video team owns the upload: video assets are produced by this team. The team is already in the assets, the editing software, and the Drive folder. SEO's role is the brief, not the upload.

6.5  |  AM coordination duty

AM tracks all four handoff tickets to completion. AM's monthly Account Health Review confirms all four closed for any client whose shoot was green-lit in the prior month.

If any handoff ticket misses SLA, AM escalates to the missing division's DH first. If unresolved within 48 hours of escalation, AM escalates to COO.

Section 7  |  Cross-division RACI and handoff SLAs

New in v6. Absorbs the work the WEB Charter v2 was waiting on. Cross-division RACI definitions, client communication boundaries, and landing page handoff standards. These are company-wide standards and live at the MasterOps layer rather than in any single Charter.

7.1  |  Cross-division RACI matrix

R = Responsible (does the work). A = Accountable (owns the outcome). C = Consulted. I = Informed.

| WORK ITEM | AM | SEO | ADS | WEB | VIDEO | MO |
| --- | --- | --- | --- | --- | --- | --- |
| Client communication | R/A | I | I | I | I | I |
| Ticket submission | R/A | I | I | I | I | I |
| SEO content writing | I | R/A | - | - | - | - |
| Web page publishing | I | C/A | - | R | - | - |
| Campaign launch (no GHL) | I | - | R/A | C | - | - |
| Campaign launch (with GHL) | I | - | R | C | - | A |
| Verified Live confirmation | I | - | C | C | - | R/A |
| Video shoot scheduling | C | C | C | C | R/A | - |
| Pre-Shoot Roadmap compilation | I | C | C | C | R/A | - |
| Green Light Trigger | I | I | I | I | R/A | - |
| YouTube brief authoring | I | R/A | - | - | C | - |
| YouTube upload execution | I | C | - | - | R/A | - |
| Vlog transcription + blog publishing | C | R/A | - | R | I | - |
| Photo extraction + GBP upload | I | R/A | C | - | I | - |
| LSA sync confirmation | I | C | R/A | - | - | - |
| Landing page build | I | C | C/A | R | - | - |
| Tracking install on website | I | I | C | R/A | - | C |
| GHL configuration | I | - | C | C | - | R/A |
| Chatbot install (website side) | I | - | - | R/A | - | C |
| Chatbot configuration | I | - | - | C | - | R/A |
| GBP status change notification | I | R/A | I | - | - | - |
| Onboarding stage execution | I | R | R | R | R | R |
| Onboarding stage coordination | C | I | I | I | I | I |

7.2  |  Handoff SLA cutoff times

Defined cutoff times for cross-division handoffs. Missing the cutoff triggers re-baselining of downstream timelines.

Landing page handoff (Paid Ads to Web Dev)

| INPUT | FROM | CUTOFF | CONSEQUENCE OF MISS |
| --- | --- | --- | --- |
| Approved brief (purpose, audience, conversion goal) | Paid Ads (Manuel) via AM ticket | 10 business days before campaign launch | Launch date moves by the same number of days as the delay. |
| Copy (headlines, body, CTAs, legal) | Paid Ads + Graphic Designer | 7 business days before campaign launch | Same. |
| Assets (images, video, brand files) | Paid Ads via Drive folder | 7 business days before campaign launch | Same. |
| Integrations (forms, GHL routing, tracking) | Mo + Paid Ads | 5 business days before campaign launch | Joint test cannot complete in time. Verified Live not granted. AM does not communicate live to client. |
| Final launch requirements (geo, budget, schedule) | Paid Ads via AM | 3 business days before campaign launch | Web Dev cannot finalize landing page configuration. |

Pre-Shoot Roadmap handoff (consuming divisions to Vince)

| INPUT | FROM | CUTOFF | CONSEQUENCE OF MISS |
| --- | --- | --- | --- |
| SEO Video-to-Page Map (S-VIDEOMAP) | Alejandro | 2 weeks before shoot | Vince escalates to COO. Shoot does not proceed without complete Roadmap. |
| Paid Ads Creative Asset List (A-PRESHOOT) | Manuel | 2 weeks before shoot | Same. |
| LSA Photo Capture List | Alejandro | 1 week before shoot | Same. |
| Web Dev Page Readiness | Justin | 1 week before shoot | Same. |
| Onboarding Manager confirmation (new clients only) | Marlo | 1 week before shoot | Same. |

Green Light handoff (Vince to consuming divisions)

| TICKET | OWNER | SLA FROM GREEN LIGHT | CONSEQUENCE OF MISS |
| --- | --- | --- | --- |
| V-YOUTUBE (prerequisite) | Video team | 48 hours | Tickets 1, 2, 3 cannot complete. AM escalates to Vince first, then COO at 48hr. |
| S-VLOG-PUB | SEO + Web Dev | 5 business days | AM escalates to Alejandro and Justin at SLA breach, then COO at 48hr unresolved. |
| W-VIDEOEMBED | Web Dev | 48 hours from YouTube upload | AM escalates to Justin at SLA breach, then COO at 48hr unresolved. |
| A-CAMPAIGN-ACT | Paid Ads | 5 business days | AM escalates to Manuel at SLA breach, then COO at 48hr unresolved. |
| S-PHOTOEXTRACT | SEO | 48 hours | Blocks LSA refresh. AM escalates to Alejandro at SLA breach, then COO at 48hr unresolved. |

7.3  |  Client communication boundaries

Default and exceptions AMs own client relationship including communication. AMs are the default client-facing voice. Division Heads and Mo join client calls only when genuinely necessary for technical depth, strategic input, or shoot logistics. Default: AM runs the call. Exception: AM brings DH or Mo in for a specific reason. Documented exceptions (such as Potomac, where Manuel is involved per Founder's prior request) remain in effect until explicitly retired. Division Heads and Mo do not communicate recurring process findings directly to clients. All findings flow through the AM.

Section 8  |  TTR Protocol  |  Time To Resolution

New in v6. Defines acknowledge SLAs, resolve SLAs, and escalation timelines for every ticket category and emergency type across all divisions. This is the company-wide standard. Division Playbooks reference this Section.

8.1  |  SLA tiers

| TIER | WHEN TO USE | ACKNOWLEDGE SLA | RESOLVE SLA |
| --- | --- | --- | --- |
| Standard | Planned requests. New builds. Changes to non-underperforming campaigns. Routine work. | End of business day | Per ticket category (24-72 hours typical) |
| Accelerated (Fast-Track) | Active campaign optimizations. Creative swaps tied to live campaign with performance signal. | 2 business hours | 4-8 hours from complete brief |
| Critical / Urgent | Client harm imminent or in progress. Significant client impact pending. | Same business day | Per category. Same day for actively wasting budget. 4 hours for tracking down. 48 hours for site outages. |
| Emergency / SOS | Client harm happening now. Site down. Account suspended. Lead capture broken. Wrong offer live. | 1 hour | Same day for site/lead/payment. 4 hours for GBP suspension. Update every 2 hours until resolved. |

8.2  |  Acknowledge SLA escalation

Escalation timeline if acknowledgement SLA breached Standard: AM checks ticket, then DMs Division Head at SLA breach + 4 hours. Accelerated: AM DMs Division Head at SLA breach + 1 hour. Critical / Urgent: AM DMs COO at SLA breach + 2 hours. Emergency / SOS: AM DMs COO immediately if no acknowledgement within 1 hour. Do not wait for the 2-hour mark.

8.3  |  Resolve SLA escalation

Resolve SLAs vary by ticket category. Each Division Playbook Section 4 has the full table. The escalation logic below applies regardless of category.

| SCENARIO | WHO TO ESCALATE TO | WHEN |
| --- | --- | --- |
| Resolve SLA missed by Division Head | COO via Slack DM | At SLA breach + 24 hours if no resolution |
| DH unresponsive after escalation | COO via Slack DM with peer DH on the escalation | Immediately |
| Cross-division blocker (waiting on another division) | Both DHs simultaneously | At blocker identification |
| GHL Verified Live blocking campaign launch | Mo + Manuel + COO | At any sign of friction with the joint test or Verified Live confirmation |
| Site down or lead capture broken | Justin + COO immediately | At identification. Emergency authority active per WEB Charter. |
| GBP suspended | Alejandro + Manuel (LSA dependency) + COO | At identification |

8.4  |  Severity definitions

| SEVERITY | DEFINITION | ESCALATION STANDARD |
| --- | --- | --- |
| SEV-1 Critical | Active client harm happening now. Site down, confirmed security breach, data loss, complete launch failure against committed date, GBP suspended, lead capture broken. | Escalate to COO immediately. Containment authority active where applicable. Updates every 2 hours until resolved. |
| SEV-2 High | Significant client impact imminent or in progress. Partial outage, degraded performance, landing page launch at risk, team capacity crisis, campaign actively wasting budget. | Escalate to COO same day. Updates every 4 hours during business hours. |
| SEV-3 Moderate | Material issue with defined resolution path. Missed build milestone, performance issue with the team, cross-division conflict not resolvable peer-to-peer. | Escalate to COO within 48 hours with proposed resolution. |
| SEV-4 Low | Process or planning concern. Scope creep pattern, capacity trend, tooling limitation. | Raise at next bi-weekly 1:1 with COO. |

8.5  |  Joint test protocol with Mo

Standard for any work that includes a GHL component. Lifted from Paid Ads Playbook v3.1 because it applies to any division initiating GHL-routed work.

| # | STEP | WHO |
| --- | --- | --- |
| 1 | Originating division builds the work on their platform side. Tags Mo when ready for joint test. | Originating division (Manuel for Paid Ads, Justin for Web Dev integrations) |
| 2 | Mo confirms GHL routing is configured: pipeline placement, automation rules, notification routing. | Mo |
| 3 | Originating division and Mo run joint test: real test lead/event submitted through the work. Both confirm end-to-end flow. | Originating division + Mo |
| 4 | Mo marks Verified Live in the ticket. Closes the GHL ticket. | Mo |
| 5 | Originating division ticket can be marked ready for launch. AM authorizes launch and communicates to client. | Originating division + AM |

Section 9  |  Document lifecycle and patch authoring

New in v6. Documents the standards for how operating-system documents are versioned, named, and patched. Closes Pattern 1 from the Pass 1.5 audit (universal predecessor-footer artifact across patched docs).

9.1  |  File ID stability doctrine

File IDs in Google Drive are stable across versions. When a document is patched, the file ID does not change. This protects every existing cross-reference URL across the operating system from breaking.

File ID stability rule Patches happen in place. The file is updated, not replaced. Cross-reference URLs throughout the operating system point to file IDs, not titles. URLs continue to work after a patch. Drive title is the visible identifier. Internal version is the doctrinal identifier. They must match.

9.2  |  OPTION 3 Drive title rename doctrine

On every patch sprint, Drive titles are renamed to match internal versions. This eliminates the gap where a patched document's Drive title says 'v2' but the internal version says 'v2_1'.

Naming convention

- Use underscore convention for sub-versions: v5_1 not v5.1, v2_2 not v2.2.

- Rename Drive title at the same time the internal version increments.

- Backfill applies to existing patched docs in the next patch wave.

Backfill schedule (in flight)

Six existing patched docs need title rename to match internal versions. Scheduled for Wave 2 of current sprint:

- MasterDirectory: Drive title to v2_2

- MasterProcess: Drive title to v5_1

- AM Playbook: Drive title to v2_1

- ADS Playbook: Drive title to v3_1

- SEO Playbook: Drive title to v4_1

- OnboardingManager: Drive title to v2 (already matches; verify)

9.3  |  Patch authoring template standard

Closes Pattern 1 from the Pass 1.5 audit. 8 of 8 patched docs across the operating system carry a trailing predecessor footer line. This is a systematic authoring artifact, not a one-off mistake.

Predecessor footer paragraph is REPLACED, not preserved When a document is patched, the footer block contains exactly one footer paragraph: the current version. The predecessor footer paragraph is REPLACED, not preserved alongside the new one. Two footer paragraphs in a document indicate authoring error. Strip the predecessor on next patch. This standard applies to every operating-system document at TSD: MasterOps, MasterDirectory, MasterProcess, division Playbooks, Charters, and Overlays.

9.4  |  Reading order for any division

When a team member needs to understand how a division operates, the reading order is:

- Brandformance Overlay (the WHY)

- Division Head Operating Charter (the SEAT and authority)

- Division Playbook (the HOW)

- MasterOps Playbook v6 (cross-division context)

9.5  |  Document layer hierarchy

Three doctrinal layers above the operational layer. Each defines a different scope.

| LAYER | SCOPE | EXAMPLES |
| --- | --- | --- |
| Master (company-wide) | Operating principles, cross-division coordination, ticketing standards, RACI, TTR. | MasterOps Playbook, MasterDirectory, MasterProcess, OrgChart, Brandformance Doctrine, Cradle to Grave. |
| Division (per-division) | How the division operates day to day. Tickets, recurring SOPs, onboarding stages. | Division Playbooks (CS AM, OnboardingManager, SEO, ADS, WEB, VIDEO). Brandformance Overlays. Division Head Charters. |
| Specialist (peer seat) | Specialist seat that operates peer-to-peer with divisions. | GHL Role Definition (Mo). |
| Operational (in-system) | Real-time work happening in tools. Tickets, automations, messages. | ClickUp tickets, Agency Titan workflows, Slack DMs, GHL configurations. |

Section 10  |  Communications and reporting

How we communicate  |  The standards

| CHANNEL | USE IT FOR | DO NOT USE IT FOR |
| --- | --- | --- |
| Tickets | All structured deliverable requests. The official record of what was asked, who owns it, when it is due. | Emergencies. General questions. Status chasing. Anything that does not require a deliverable from another unit. |
| Slack DM | Emergencies. Direct escalation to Division Head, Mo, or COO. Proactive issue notifications from DHs or Mo to AMs. | Ticket submissions. Requests that belong in the ticket system. |
| Slack Channel | Team-wide announcements. Division-wide updates. Friday Pulse posts (#paid-ads-pulse, #seo-pulse, #webdev-pulse). | Back-and-forth requests. Anything that needs a response from a specific person. |
| Friday Status Update | Weekly reporting from all AMs to the CS DH and all DHs (and Mo) to the COO by 4 PM Friday. Incorporates Pulse rows from Aggregator Block. | Ad hoc status questions. |
| Email | External client communication when client preference is email. Some external partners. | Internal team communication. |

Client communication AMs own client relationship including communication. AMs are the default client-facing voice. Division Heads and Mo join client calls only when genuinely necessary. Documented exceptions (such as Potomac, where Manuel is involved per Founder's prior request) are documented in the relevant division docs.

How we stay accountable  |  Reporting structure

This is not a flat organization. Everyone has a lane, everyone has a reporting line, and everyone is accountable to the standards in this document.

| ROLE | REPORTS TO | ACCOUNTABLE FOR |
| --- | --- | --- |
| Account Managers | CS Division Head | Client relationship health (including communication), project coordination across divisions, ticket quality, deliverable tracking, recurring process output communication to client, Aggregator Block consumption, Friday status updates, Red row 48hr triage. |
| Onboarding Manager | CS Division Head | Onboarding pipeline execution, Agency Titan accuracy, client communication channel management, Pre-Shoot Roadmap input #5 for new clients. |
| CS Division Head | COO | AM performance, onboarding completion, client retention signals, division process compliance. |
| SEO Division Head | COO | SEO deliverable volume and quality, GBP optimization, content plan execution, Monthly SEO Optimization output to AMs, R9 Weekly SEO Pulse, R10 Quarterly SEO Strategy Review, YouTube brief authoring, Pre-Shoot Roadmap inputs 1 and 3. |
| Paid Ads Division Head | COO | Campaign performance, SLA compliance, proactive AM communication, budget discipline, joint test participation with Mo, A4 Weekly Paid Ads Pulse, A5 Quarterly Paid Ads Strategy Review, Graphic Designer management, Pre-Shoot Roadmap input 2. |
| Web Dev Division Head | COO | Website infrastructure uptime, publishing SLAs, dashboard integrity, tracking install on the website, W4 Weekly Web Dev Pulse, Pre-Shoot Roadmap input 4, emergency authority during active incidents. |
| GHL Integrations Specialist (Mo) | COO | All GHL configuration, Verified Live confirmations, joint test execution, GHL emergency response. |
| Creative / Video Division Head | COO | Shoot execution, edit turnaround times, video delivery SLAs, Pre-Shoot Roadmap compilation, Green Light Trigger, YouTube upload execution. |
| All Division Heads + Mo | COO | Friday status update by 4 PM. Ticket acknowledgement per TTR Protocol Section 8. Recurring process execution per Playbook Section 5. |

Section 11  |  What is still in progress

The following items are not yet finalized. They will be updated as decisions are made.

| ITEM | OWNER | STATUS |
| --- | --- | --- |
| Web Dev Playbook v3 Section 5 (W1/W2/W3 Recurring SOPs) Justin review and confirmation | Justin + COO | DRAFT pending review. Targeted for Wave 3 (Division Playbook patch wave) of current sprint. |
| Charter v3 wave (SEO, VIDEO) for YouTube doctrine resolution | COO + Alejandro + Vince | Wave 4 of current sprint. Runs after MasterOps v6 ships. |
| Overlay v3 wave (SEO, VIDEO) for YouTube doctrine resolution | COO + Alejandro + Vince | Wave 4 of current sprint. |
| Reporting platform Founder async confirmation (Agency Analytics default) | Founder | Async pending. |
| AT Process Specs for all recurring processes + onboarding master | Separate sprint | Deferred to dedicated AT chat. |
| TSD Onboarding Portal (Web Dev build) | Justin + team | In progress, phased. |
| Tier reconciliation for clients receiving email outside their tier (Mission Accomplished, Neon Monkey, Napps, Watt's Right) | AMs + CS DH + COO | Pending AM conversation. |
| Brandformance Readiness Assessment (Potomac structural fix) | COO + Founder | Parked. Targeted week of May 4. |
| Social media publishing permanent ownership (non-YouTube) | COO | Transitional. AM bridge today. Target structural fix Q3 2026. YouTube ownership resolved in v6 (Video team). |
| Email and text marketing permanent ownership | COO | Transitional. AM bridge today. Target structural fix Q3 2026. |
| DH on client calls phase-out | COO | In progress. Exceptions documented (Potomac). |
| Press Release calendar link confirmation | Onboarding Manager | Pending. |
| Matthew Riccardi separation execution | COO + Angela | Confirmed but not yet executed. Angela consulted first. |

Version 6 supersedes Version 5. All Patch Memos absorbed. Cross-division video workflow, weekly Pulses, quarterly Strategy Reviews, AM Aggregator Block, RACI matrix, handoff SLA cutoff times, TTR Protocol, and document lifecycle doctrine are now first-class citizens of the operating system.